## C-1226-45-07-01-01-001
SCHEDULE
Name of the work: Providing of ERO store room roof with galvalume sheet, Flooring with vetrified tiles, False ceiling for JAO & PBA room, Painting & necessary electrical items to ERO Store Room shed on existing first floor of ERO-Gadwal at Jogulamba Gadwal District.WBS No.C-1226-45-07-01-01-001.
|  |  | Face Value |  | 197657
Sl No | Service Code | Description of work | Qty | Unit | Rates per Unit | Amount
1 | SWR33402 | Roofing with Trapezoidal/GalvalumeSheet | 65.251 | M2 | 577.47 | 37680.495
2 | SWR33223 | Vitrified Tile Flooring 38mm CM(1:3) | 42.739 | M2 | 887 | 37909.493
3 | SWR33238 | Vitrified Tile Skirting CM(1:3) | 3.934 | M2 | 877 | 3450.118
4 | SWR33390 | False Ceiling-Gypoard Fine Line Grid | 25.357 | M2 | 941.73 | 23879.4476
5 | SWR33015 | Excavation in Ordinary Soil | 3.483 | M3 | 347 | 1208.601
6 | SWR33028 | PCC with 40mm Metal (1:4:8) | 3.487 | M3 | 4451 | 15520.637
7 | SWR33559 | S&F 9W LED Lamp | 5 | EA | 150 | 750
8 | SWR33564 | S&F Electronic Regulator for Ceiling Fan | 4 | EA | 565 | 2260
9 | SWR33264 | S&F MT Wood Frame & Door-Laminate | 5.433 | M2 | 6799 | 36938.967
10 | SWR33333 | Painting with OBD 2Coats+Primer | 185.563 | M2 | 109.9 | 20393.3737
11 | SWR33364 | Paint-PlasticEmulsn2Coat+Primer-Extrnl1F | 91.653 | M2 | 187.86 | 17217.9326
12 | SWR34470 | Seigniorage Charges - Sand | 3.378 | M3 | 40 | 135.12
13 | SWR34471 | Seigniorage Charges - Metal | 3.208 | M3 | 97.5 | 312.78
GRAND TOTAL | [5 empty] | 197656.9649
Conditions :
1 | The Contractor will have provide his own labour, T&P and Sub-Transport up to 10 km at his cost and above 10 km will be paid as per SSR.
2 | The Work Should be carried out as per APSDD Rules
3 | The Contractor will be responsible for any accident to any of his workers and liability that may arise for payment of compensation under provision of act of A.P.
4 | The Work Should be done in the presence of AEE/Civil/Gadwal
5 | The Work Should be completed with in 60 Days from the Handover of site
6 | Agreement concluded with available SSR-2024-25 codes
Signature of the Contractor. |  |  |  | Superintending Engineer
Operation Gadwal.
COMPARATIVE STATEMENT
The Rates quoted by M/s Vijetha Electrical Constructions, Wanaparthy Has Quoted lowest rates. Hence accepted.
Sl No | Service Code | Description of work | Qty | Unit | SSR Rates per Unit
The Rates quoted by Mr. Ravendra Goud, Contractor, K.R.Cheruvu has quoted lowest rates. Hence accepted.
The Rates quoted by Mr. Sreenivasa Goud, Contractor, Shanthinagar has quoted lowest rates. Hence accepted.
The Rates quoted by Mr. E.Nagendra, Contractor, Kurnool has quoted lowest rates. Hence accepted.
The Rates quoted by M/s Vijetha Electricals, Contractor, Wanaparthy has quoted lowest rates. Hence accepted.
The Rates quoted by M/s Harika Electricals, Contractor, Ieeza has quoted lowest rates. Hence accepted.
The Rates quoted by Mr. Praveen Kumar, Contractor, Gadwal has quoted lowest rates. Hence accepted.
| Rates quoted by the Contractor | Amount quoted by the Contractor
Sub-Total:
12.36 % Service tax: | [5 empty] | 0
Total: | [5 empty] | 0
Sri Raghavendra Goud, Civil & Electrical contractor, H. No. 2-21, K.R Cheruvu, Maldakal
Sri E.Nagendra, Contractor, Electrical & Civil Works, H. No. 40-310A, Bhagyanagar, Kurnool
M/s Vijetha Electrical Constructions, H. No. 42-187/6, Vengalrao Colony, Wanaparthy
Sri S.E.Sreenivasa Goud, Contractor, Electrical&Civil Works, Shanthinagar vg., Waddepally M